## ExtPb
External Problems
| Risk Description | Probability | Impact | Rank | Solution Description
1 | Poor Knowledge of image rights |  |  |  | Using only Public DataSet
2 | Misuse of the application |  |  |  | Develop guides in the application to help users
3 | Incorrect Database data |  |  |  | Ensure a high-quality by collecting data with variations in resolution, angles and light conditions
4 | Embedding Model Performance |  |  |  | Use transfer learning or fine-tune models on the specific dataset used by the application
5 | Lighting and Environmental Variations |  |  |  | Develop preprocessing techniques like adaptive equalization
6 | Mobile Device Compatibility |  |  |  | Test the app on a wide range of devices
7 | Low Network Availability |  |  |  | Implement offline support and sync result when the network is available
8 | Permission of the Museum |  |  |  | Collaborate with museum administrations to clarify usage permissions and promote the app as a beneficial tool.
9 | Not Direct access to the Painting |  |  |  | Include description to the painting in the app, so the user don't have to get that close

## IntTechPb
Internal Technical Problems
| Risk Description | Probability | Impact | Rank | Solution Description
1 | Incomplete visual rendering |  |  |  | HardCoding to see a result of the application
2 | Incomplete Data Matching |  |  |  | HardCoding to see a result of the application
3 | Difficulties in adopting new technologies |  |  |  | Share knowledge of technologies between teamMember
4 | Data Security |  |  |  | Use encryption and obfuscation techniques to protect the deployed model.
5 | Intergration Issues |  |  |  | Use an API first approach to have a clear design, and Adopt a microservices architecture
6 | Wrong result by scanning the tables |  |  |  | Implement a multi-stage verification process, and can also return "No match found"
7 | DataBase Scalability |  |  |  | Use optimized databases like Faiss
8 | Deployment Issues |  |  |  | Use containerization tools like Docker or Kubernetes
9 | Inconsistent Code Quality |  |  |  | Enforce coding standards, use a shared Git repository

## IntNTechPb
Internal Non-Technical Problems
| Risk Description | Probability | Impact | Rank | Solution Description
1 | Poor Time Management |  |  |  | Use task management tools and follow clear milesstones
2 | Team Conflicts |  |  |  | Clearly define roles and responsibilities
3 | Communication Breakdown |  |  |  | Use communication platforms and regular discussions about progress and issues
4 | Unrealistic Expectations |  |  |  | Define a MVP and consider deature additions later
5 | Knowledge Gaps |  |  |  | Divide tasks based on strengths and encourage peer or team learning
6 | Presentation and Demo Challenges |  |  |  | Prepare a structured presentation with visuals, an app demo, and show functionality
7 | Lack of Productivity |  |  |  | Encourage breaks and short but efficient working sessions
8
9

## AllPb
All Possible Problems
|  | Risk Description | Probability | Impact | Rank | Solution Description
External Problems | 1 | Poor Knowledge of image rights | 2 | 1 |  | Using only Public DataSet
| 2 | Misuse of the application | 3 | 4 |  | Develop guides in the application to help users
| 3 | Incorrect Database data | 2 | 3 |  | Ensure a high-quality by collecting data with variations in resolution, angles and light conditions
| 4 | Embedding Model Performance | 1 | 3 |  | Use transfer learning or fine-tune models on the specific dataset used by the application
| 5 | Lighting and Environmental Variations | 3 | 2 |  | Develop preprocessing techniques like adaptive equalization
| 6 | Mobile Device Compatibility | 3 | 3 |  | Test the app on a wide range of devices
| 7 | Low Network Availability | 2 | 2 |  | Implement offline support and sync result when the network is available
| 8 | Permission of the Museum | 2 | 4 |  | Collaborate with museum administrations to clarify usage permissions and promote the app as a beneficial tool.
| 9 | Not Direct access to the Painting | 3 | 1 |  | Include description to the painting in the app, so the user don't have to get that close
Internal Technical Problems | 10 | Incomplete visual rendering | 1 | 2 |  | HardCoding to see a result of the application
| 11 | Incomplete Data Matching | 1 | 4 |  | HardCoding to see a result of the application
| 12 | Difficulties in adopting new technologies | 4 | 4 |  | Share knowledge of technologies between teamMember
| 13 | Data Security | 1 | 5 |  | Use encryption and obfuscation techniques to protect the deployed model.
| 14 | Intergration Issues | 4 | 3 |  | Use an API first approach to have a clear design, and Adopt a microservices architecture
| 15 | Wrong result by scanning the tables | 2 | 5 |  | Implement a multi-stage verification process, and can also return "No match found"
| 16 | DataBase Scalability | 1 | 1 |  | Use optimized databases like Faiss
| 17 | Deployment Issues | 3 | 5 |  | Use containerization tools like Docker or Kubernetes
| 18 | Inconsistent Code Quality | 4 | 2 |  | Enforce coding standards, use a shared Git repository
Internal Non-Technical Problems | 19 | Poor Time Management | 4 | 5 |  | Use task management tools and follow clear milesstones
| 20 | Team Conflicts | 5 | 4 |  | Clearly define roles and responsibilities
| 21 | Communication Breakdown | 5 | 5 |  | Use communication platforms and regular discussions about progress and issues
| 22 | Unrealistic Expectations | 5 | 3 |  | Define a MVP and consider deature additions later
| 23 | Knowledge Gaps | 5 | 1 |  | Divide tasks based on strengths and encourage peer or team learning
| 24 | Presentation and Demo Challenges | 4 | 1 |  | Prepare a structured presentation with visuals, an app demo, and show functionality
| 25 | Lack of Productivity | 5 | 2 |  | Encourage breaks and short but efficient working sessions

## Matrix
5 | 23 | 25 | 22 | 20 | 21
4 | 24 | 18 | 14 | 12 | 19
3 | 9 | 5 | 6 | 2 | 17
2 | 1 | 7 | 3 | 8 | 15
1 | 16 | 10 | 4 | 11 | 13
Probability Impact | 1 | 2 | 3 | 4 | 5